## Prod Planning Plant 5 & 6(D365)
Production Plan (NGC)
Month of Production : July 2025 |  | Prepared by : Aziani |  |  |  |  | Date : 27 June 2025
Revision # : 0
Production Plant : 5
|  | Former Size by tier (7523pcs of formers per tier) |  |  |  | Period of Production
NGC Line # | Glove Code | LB | LT | RB | RT | Start Date | End Date | CPD Version | Remark
49 | NB-AB-OLPF-033-SE-VIOL-ASTM | L | L | L | L | 2025-07-01 | 2025-07-03 | CPD-NB-KM01-VIOL-08 (4HSD, 0.261857B, WAX4)
| NB-AB-OLPF-027-SE-WHTE-ASTM | L | L | L | L | 2025-07-04 | 2025-07-05 | CPD-NB-LG01-WHTE-11 (WAX4)
| NB-AB-OLPF-030-SE-VBLU-EN6N | XL | L | L | L | 2025-07-06 | 2025-07-10 | CPD-NB-NT06-VBLU-22 (4R086A,WAX4,VBL2)
| NB-AB-OLPF-034-SE-VBLU-EN6N | XL | L | L | L | 2025-07-11 | 2025-07-17 | CPD-NB-KM01-VBLU-33 (4R086A,VBL2,WAX4)
| NB-AB-OLPF-027-SE-DKBU-ASTM | XL | L | L | L | 2025-07-18 | 2025-07-20 | CPD-NB-KM01-DKBU-27 (WAX4)
| PENDING ORDER |  |  |  |  | 2025-07-21 | 2025-07-31
50 | NB-AB-OLPF-030-SE-DKBU-EN6N | S | S | S | S | 2025-07-01 | 2025-07-01 | CPD-NB-NT06-DKBU-16 (4R086A,0.7TiO2,WAX4)
| NB-AB-OLPF-027-SE-DKBU-ASTM | S | S | S | S | 2025-07-02 | 2025-07-06 | CPD-NB-KM01-DKBU-27 (WAX4) | 4
| NB-AB-OLPF-027-SE-WHTE-ASTM | S | S | XS | XS | 2025-07-07 | 2025-07-10 | CPD-NB-LG01-WHTE-11 (WAX4)
| NB-AB-OLPF-034-SE-WHTE-EN6N | S | S | XS | XS | 2025-07-11 | 2025-07-17 | CPD-NB-LG01-WHTE-12 (4HSD,WAX4)
| NB-AB-OLPF-034-SE-VBLU-EN6N | S | S | XS | XS | 2025-07-18 | 2025-07-22 | CPD-NB-KM01-VBLU-33 (4R086A,VBL2,WAX4)
| NB-AB-OLPF-034-SE-VBLU-EN6N | S | S | S | S | 2025-07-23 | 2025-07-26 | CPD-NB-KM01-VBLU-33 (4R086A,VBL2,WAX4)
| PENDING ORDER |  |  |  |  | 2025-07-27 | 2025-07-31
51 | NB-AB-OLPF-027-SE-DKBU-ASTM | S | S | M | M | 2025-07-01 | 2025-07-05 | CPD-NB-KM01-DKBU-27 (WAX4)
| NB-AB-OLPF-034-SE-WHTE-EN6N | S | S | M | M | 2025-07-06 | 2025-07-17 | CPD-NB-LG01-WHTE-12 (4HSD,WAX4) | 11
| NB-AB-OLPF-032-SE-WHTE-EN6N | S | S | M | M | 2025-07-18 | 2025-07-31 | CPD-NB-KM01-WHTE-17 (4R086A, 2.0TiO2, WAX4)
52 | NB-AB-OLPF-027-SE-DKBU-ASTM | S | S | S | XS | 2025-07-01 | 2025-07-03 | CPD-NB-KM01-DKBU-27 (WAX4)
| NB-AB-OLPF-030-SE-VBLU-EN6N | S | S | S | XS | 2025-07-04 | 2025-07-06 | CPD-NB-NT06-VBLU-22 (4R086A,WAX4,VBL2)
| NB-AB-OLPF-034-SE-VBLU-EN6N | S | S | S | XS | 2025-07-07 | 2025-07-19 | CPD-NB-KM01-VBLU-33 (4R086A,VBL2,WAX4)
| NB-AB-OLPF-032-SE-WHTE-EN6N | S | S | S | XS | 2025-07-20 | 2025-07-25 | CPD-NB-KM01-WHTE-17 (4R086A, 2.0TiO2, WAX4)
| NB-AB-OLPF-027-SE-MTBU-ASTM | S | S | S | XS | 2025-07-26 | 2025-07-27 | CPD-NB-LG01-MTBU-02 (WAX4)
| NB-AB-OLPF-027-SE-MTBU-ASTM | S | S | S | S | 2025-07-28 | 2025-07-31 | CPD-NB-LG01-MTBU-02 (WAX4)
53 | NB-AB-OLPF-032-SE-MTBU-ACCF | S | S | M | M | 2025-07-01 | 2025-07-03 | CPD-NB-KM01-MTBU-10 (4R086A, 1.0ZnO,ATO2, WAX4)
| NB-AB-OLPF-032-SE-MTBU-ACCF | S | S | M | XS | 2025-07-04 | 2025-07-05 | CPD-NB-KM01-MTBU-10 (4R086A, 1.0ZnO,ATO2, WAX4)
| NB-AB-OLPF-032-SE-MTBU-ACCF | S | S | S | S | 2025-07-06 | 2025-07-08 | CPD-NB-KM01-MTBU-10 (4R086A, 1.0ZnO,ATO2, WAX4)
| NB-AB-OLPF-027-SE-WHTE-ASTM | S | S | S | S | 2025-07-09 | 2025-07-13 | CPD-NB-LG01-WHTE-11 (WAX4)
| MODIFICATION WORK - HIK & CLEANING AREA |  |  |  |  | 2025-07-14 | 2025-07-19
| PENDING ORDER |  |  |  |  | 2025-07-20 | 2025-07-31
54 | NB-AB-OLPF-027-SE-MTBU-ASTM | XL | XL | L | L | 2025-07-01 | 2025-07-01 | CPD-NB-LG01-MTBU-02(WAX4)
| NB-AB-OLPF-034-SE-VBLU-EN6N | XL | XL | L | L | 2025-07-02 | 2025-07-18 | CPD-NB-KM01-VBLU-33 (4R086A,VBL2,WAX4)
| NB-AB-OLPF-032-SE-WHTE-EN6N | XL | XL | L | L | 2025-07-19 | 2025-07-28 | CPD-NB-KM01-WHTE-17 (4R086A, 2.0TiO2, WAX4)
| NB-AB-OLPF-032-SE-WHTE-EN6N | L | L | L | L | 2025-07-29 | 2025-07-31 | CPD-NB-KM01-WHTE-17 (4R086A, 2.0TiO2, WAX4)
55 | NB-AB-OLPF-033-SE-VIOL-ASTM | S | S | S | S | 2025-07-01 | 2025-07-08 | CPD-NB-KM01-VIOL-08 (4HSD, 0.261857B, WAX4)
| NB-AB-OLPF-027-SE-DKBU-ASTM | S | S | S | S | 2025-07-09 | 2025-07-15 | CPD-NB-KM01-DKBU-27 (WAX4)
| NB-AB-OLPF-027-SE-DKBU-ASTM | S | S | S | XS | 2025-07-16 | 2025-07-28 | CPD-NB-KM01-DKBU-27 (WAX4)
| PENDING ORDER |  |  |  |  | 2025-07-29 | 2025-07-31
56 | NB-AB-OLPF-032-SE-VBLU-EN6N | M | M | M | M | 2025-07-01 | 2025-07-03 | CPD-NB-NT06-VBLU-23 (4R086A,WAX4,VBL2)
| NB-AB-OLPF-034-SE-VBLU-EN6N | M | M | M | M | 2025-07-04 | 2025-07-20 | CPD-NB-KM01-VBLU-33 (4R086A,VBL2,WAX4)
| NB-AB-OLPF-027-SE-MTBU-ASTM | M | M | M | M | 2025-07-21 | 2025-07-31 | CPD-NB-LG01-MTBU-02(WAX4)
57 | NB-AB-OLPF-034-SE-VBLU-EN6N | M | M | M | M | 2025-07-01 | 2025-07-21 | CPD-NB-KM01-VBLU-33 (4R086A,VBL2,WAX4)
| PENDING ORDER |  |  |  |  | 2025-07-22 | 2025-07-31
58 | NB-AB-OLPF-027-SE-MTBU-ASTM | S | S | S | S | 2025-07-01 | 2025-07-04 | CPD-NB-LG01-MTBU-02(WAX4)
| NB-AB-OLPF-034-SE-VBLU-EN6N | S | S | S | S | 2025-07-05 | 2025-07-20 | CPD-NB-KM01-VBLU-33 (4R086A,VBL2,WAX4)
| PENDING ORDER |  |  |  |  | 2025-07-21 | 2025-07-31
59 | NB-AB-OLPF-027-SE-MTBU-ASTM | M | M | M | M | 2025-07-01 | 2025-07-01 | CPD-NB-LG01-MTBU-02(WAX4)
| MODIFICATION WORK - HIK & CLEANING AREA |  |  |  |  | 2025-07-02 | 2025-07-07
| NB-AB-OLPF-027-SE-WHTE-ASTM | M | M | M | M | 2025-07-08 | 2025-07-12 | CPD-NB-LG01-WHTE-11 (WAX4)
| NB-AB-OLPF-034-SE-VBLU-EN6N | M | M | M | M | 2025-07-13 | 2025-07-21 | CPD-NB-KM01-VBLU-33 (4R086A,VBL2,WAX4)
| NB-AB-OLPF-032-SE-WHTE-EN6N | M | M | M | M | 2025-07-22 | 2025-07-31 | CPD-NB-KM01-WHTE-17 (4R086A, 2.0TiO2, WAX4)
60 | NB-AB-OLPF-033-SE-VIOL-ASTM | M | M | M | M | 2025-07-01 | 2025-07-04 | CPD-NB-KM01-VIOL-08 (4HSD, 0.261857B, WAX4)
| ANNUAL MAINTENANCE |  |  |  |  | 2025-07-05 | 2025-07-15
| MODIFICATION WORK - HIK & CLEANING AREA |  |  |  |  | 2025-07-16 | 2025-07-20
| NB-AB-OLPF-032-SE-WHTE-EN6N | M | M | M | M | 2025-07-21 | 2025-07-31 | CPD-NB-KM01-WHTE-17 (4R086A, 2.0TiO2, WAX4)
Production Plant : 6
|  | Former Size by tier (7523pcs of formers per tier) |  |  |  | Period of Production
NGC Line # | Glove Code | LB | LT | RB | RT | Start Date | End Date | CPD Version | Remark
61 | NB-AB-OLPF-030-SE-VBLU-EN6N | L | L | L | L | 2025-07-01 | 2025-07-07 | CPD-NB-KM01-VBLU-56 (4R086A,WAX4,0.27VBLU)
| NB-AB-OLPF-030-SE-VBLU-EN6N | XXL | L | L | L | 2025-07-08 | 2025-07-08 | CPD-NB-KM01-VBLU-56 (4R086A,WAX4,0.27VBLU)
| NB-AB-OLPF-032-SE-VBLU-EN6N | XXL | L | L | L | 2025-07-09 | 2025-07-09 | CPD-NB-LG01-VBLU-26 (4ESD >> 4HSD, WAX4, 0.27VBLU)
| NB-AB-OLPF-034-SE-VBLU-EN6N | XXL | L | L | L | 2025-07-10 | 2025-07-14 | CPD-NB-LG01-VBLU-26 (4ESD >> 4HSD, WAX4, 0.27VBLU)
| NB-AB-OLPF-034-SE-VBLU-BIOD | XXL | L | L | L | 2025-07-15 | 2025-07-15 | CPD-NB-KM01-VBLU-54 (BIOD, 4R086A, HV 0.27VBLU, WAX4)
| NB-AB-OLPF-034-SE-VBLU-BIOD | XL | L | L | L | 2025-07-16 | 2025-07-22 | CPD-NB-KM01-VBLU-54 (BIOD, 4R086A, HV 0.27VBLU, WAX4)
| NB-AB-OLPF-032-SE-VBLU-EN6N | XL | L | L | L | 2025-07-23 | 2025-07-24 | CPD-NB-LG01-VBLU-26 (4ESD >> 4HSD, WAX4, 0.27VBLU)
| PENDING ORDER |  |  |  |  | 2025-07-25 | 2025-07-27
| MODIFICATION WORK - CLEANING & APM INSTAL |  |  |  |  | 2025-07-28 | 2025-07-31
62 | NB-AB-OLPF-030-SE-VBLU-EN6N | M | M | M | M | 2025-07-01 | 2025-07-06 | CPD-NB-NT06-VBLU-25 (4ESD >> 4HSD, WAX4, 0.27VBLU)
| NB-AB-AMPF-030-SE-VBLU-EN6N | M | M | M | M | 2025-07-07 | 2025-07-15 | CPD-NB-NT01-VBLU-32 (4R086A,WAX4, 0.27VBLU)
| NB-AB-OLPF-034-SE-VBLU-BIOD | M | M | M | M | 2025-07-16 | 2025-07-20 | CPD-NB-KM01-VBLU-54 (BIOD, 4R086A, HV 0.27VBLU, WAX4)
| MODIFICATION WORK - CLEANING & APM INSTAL |  |  |  |  | 2025-07-21 | 2025-07-26
| PENDING ORDER |  |  |  |  | 2025-07-27 | 2025-07-31
63 | MODIFICATION WORK - CLEANING & APM INSTAL |  |  |  |  | 2025-07-01 | 2025-07-05
| NB-AB-OLPF-030-SE-WHTE-EN6N | M | M | M | M | 2025-07-06 | 2025-07-13 | CPD-NB-NT06-WHTE-21 (4R086A, 2.0TIO2, SDBS, WAX4)
| NB-AB-OLPF-034-SE-VBLU-BIOD | M | M | M | M | 2025-07-14 | 2025-07-22 | CPD-NB-KM01-VBLU-54 (BIOD, 4R086A, HV 0.27VBLU, WAX4)
| PENDING ORDER |  |  |  |  | 2025-04-23 | 2025-07-31
64 | NB-AB-AMPF-030-SE-VBLU-EN6N | S | S | S | XS | 2025-07-01 | 2025-07-02 | CPD-NB-NT01-VBLU-32 (4R086A,WAX4, 0.27VBLU)
| NB-AB-AMPF-030-SE-VBLU-EN6N | S | S | S | S | 2025-07-03 | 2025-07-07 | CPD-NB-NT01-VBLU-32 (4R086A,WAX4, 0.27VBLU)
| NB-AB-OLPF-032-SE-VBLU-EN6N | S | S | S | S | 2025-07-08 | 2025-07-13 | CPD-NB-LG01-VBLU-26 (4ESD >> 4HSD, WAX4, 0.27VBLU)
| NB-AB-OLPF-032-SE-VBLU-EN6N | S | S | S | XS | 2025-07-14 | 2025-07-16 | CPD-NB-LG01-VBLU-26 (4ESD >> 4HSD, WAX4, 0.27VBLU)
| NB-AB-OLPF-034-SE-VBLU-BIOD | S | S | S | XS | 2025-07-17 | 2025-07-23 | CPD-NB-KM01-VBLU-54 (BIOD, 4R086A, HV 0.27VBLU, WAX4)
| PENDING ORDER |  |  |  |  | 2025-07-24 | 2025-07-31
65 | NB-AB-OLPF-032-SE-DAWN-OM6N | M | M | M | M | 2025-07-01 | 2025-07-20 | CPD-NB-NT06-DAWN-05 (4HSD, WAX4)
| NB-AB-OLPF-034-SE-VBLU-EN6N | M | M | M | M | 2025-07-21 | 2025-07-25 | CPD-NB-LG01-VBLU-26 (4ESD >> 4HSD, WAX4, 0.27VBLU)
| PENDING ORDER |  |  |  |  | 2025-07-26 | 2025-07-31
66 | MODIFICATION WORK - CLEANING & APM INSTAL |  |  |  |  | 2025-07-01 | 2025-07-03
| NB-AB-OLPF-030-SE-BLCK-ASTM | S | S | S | S | 2025-07-04 | 2025-07-11 | CPD-NB-KM01-BLCK-27 (4R086A,WAX4) | Goodpac+
| NB-AB-OLPF-034-SE-VBLU-BIOD | S | S | S | S | 2025-07-12 | 2025-07-17 | CPD-NB-KM01-VBLU-54 (BIOD, 4R086A, HV 0.27VBLU, WAX4) | Goodpac+
| NB-AB-OLPF-030-SE-WHTE-EN6N | XS | XS | S | S | 2025-07-18 | 2025-07-24 | CPD-NB-NT06-WHTE-21 (4R086A, 2.0TIO2, SDBS, WAX4) | Goodpac+
| PENDING ORDER |  |  |  |  | 2025-07-25 | 2025-07-31
67 | NB-AB-OLPF-030-SE-BLCK-ASTM | M | M | M | M | 2025-07-01 | 2025-07-07 | CPD-NB-KM01-BLCK-27 (4R086A,WAX4) | Goodpac+
| NB-AB-OLPF-030-SE-BLCK-ASTM | XL | XL | L | L | 2025-07-08 | 2025-07-14 | CPD-NB-KM01-BLCK-27 (4R086A,WAX4) | Goodpac+
| NB-AB-OLPF-030-SE-BLCK-ASTM | L | L | L | L | 2025-07-15 | 2025-07-16 | CPD-NB-KM01-BLCK-27 (4R086A,WAX4) | Goodpac+
| NB-AB-OLPF-032-SE-DAWN-OM6N | L | L | L | L | 2025-07-17 | 2025-07-19 | CPD-NB-NT06-DAWN-05 (4HSD, WAX4) | Goodpac+
| NB-AB-OLPF-032-SE-DAWN-OM6N | XL | XL | L | L | 2025-07-20 | 2025-07-20 | CPD-NB-NT06-DAWN-05 (4HSD, WAX4) | Goodpac+
| NB-AB-OLPF-030-SE-VBLU-EN6N | XL | XL | L | L | 2025-07-21 | 2025-07-21 | CPD-NB-NT06-VBLU-25 (4ESD >> 4HSD, WAX4, 0.27VBLU) | Goodpac+
| NB-AB-OLPF-030-SE-VBLU-EN6N | M | M | L | L | 2025-07-22 | 2025-07-23 | CPD-NB-NT06-VBLU-25 (4ESD >> 4HSD, WAX4, 0.27VBLU) | Goodpac+
| PENDING ORDER |  |  |  |  | 2025-07-24 | 2025-07-31
68 | NB-AB-OLPF-034-SE-VBLU-BIOD | M | M | M | M | 2025-07-01 | 2025-07-10 | CPD-NB-KM01-VBLU-54 (BIOD, 4R086A, HV 0.27VBLU, WAX4) | Goodpac+
| NB-AB-OLPF-030-SE-WHTE-EN6N | M | M | S | S | 2025-07-09 | 2025-07-11 | CPD-NB-NT06-WHTE-21 (4R086A, 2.0TIO2, SDBS, WAX4) | Goodpac+
| NB-AB-OLPF-030-SE-VBLU-EN6N | M | M | S | S | 2025-07-12 | 2025-07-15 | CPD-NB-NT06-VBLU-25 (4ESD >> 4HSD, WAX4, 0.27VBLU) | Goodpac+
| NB-AB-OLPF-032-SE-DAWN-OM6N | M | M | S | S | 2025-07-16 | 2025-07-22 | CPD-NB-NT06-DAWN-05 (4HSD, WAX4) | Goodpac+
| NB-AB-OLPF-032-SE-DAWN-OM6N | M | M | M | M | 2025-07-23 | 2025-07-24 | CPD-NB-NT06-DAWN-05 (4HSD, WAX4) | Goodpac+
| PENDING ORDER |  |  |  |  | 2025-07-25 | 2025-07-31
69 | NB-AB-OLPF-032-SE-DAWN-OM6N | M | M | M | M | 2025-07-01 | 2025-07-03 | CPD-NB-NT06-DAWN-05 (4HSD, WAX4)
| NB-AB-OLPF-032-SE-DAWN-OM6N | M | M | S | S | 2025-07-04 | 2025-07-19 | CPD-NB-NT06-DAWN-05 (4HSD, WAX4)
| NB-AB-OLPF-027-SE-DCBU-ASTM | M | M | S | S | 2025-07-20 | 2025-07-24 | CPD-NB-LG01-DCBU-02 (WAX4)
| NB-AB-OLPF-027-SE-DCBU-ASTM | XS | XS | S | S | 2025-07-25 | 2025-07-25 | CPD-NB-LG01-DCBU-02 (WAX4)
| NB-AB-OLPF-027-SE-DCBU-ASTM | S | S | S | S | 2025-07-26 | 2025-07-27 | CPD-NB-LG01-DCBU-02 (WAX4)
| NB-AB-OLPF-027-SE-DCBU-ASTM | M | M | L | L | 2025-07-28 | 2025-07-29 | CPD-NB-LG01-DCBU-02 (WAX4)
| PENDING ORDER |  |  |  |  | 2025-07-30 | 2025-07-31
70 | NB-AB-AMPF-030-SE-VBLU-EN6N | XL | L | L | L | 2025-07-01 | 2025-07-02 | CPD-NB-NT01-VBLU-32 (4R086A,WAX4, 0.27VBLU)
| NB-AB-AMPF-030-SE-VBLU-EN6N | L | L | L | L | 2025-07-03 | 2025-07-05 | CPD-NB-NT01-VBLU-32 (4R086A,WAX4, 0.27VBLU)
| NB-AB-OLPF-032-SE-DAWN-OM6N | L | L | L | L | 2025-07-06 | 2025-07-17 | CPD-NB-NT06-DAWN-05 (4HSD, WAX4)
| NB-AB-OLPF-032-SE-DAWN-OM6N | XL | L | L | L | 2025-07-18 | 2025-07-20 | CPD-NB-NT06-DAWN-05 (4HSD, WAX4)
| ANNUAL MAINTENANCE |  |  |  |  | 2025-07-21 | 2025-07-31
71 | NB-AB-OLPF-030-SE-VBLU-EN6N | S | S | S | S | 2025-07-01 | 2025-07-04 | CPD-NB-NT06-VBLU-25 (4ESD >> 4HSD, WAX4, 0.27VBLU)
| MODIFICATION WORK - CLEANING & APM INSTAL |  |  |  |  | 2025-07-05 | 2025-07-10
| NB-AB-OLPF-030-SE-VBLU-EN6N | S | S | S | S | 2025-07-11 | 2025-07-18 | CPD-NB-NT06-VBLU-25 (4ESD >> 4HSD, WAX4, 0.27VBLU)
| NB-AB-OLPF-034-SE-VBLU-BIOD | S | S | S | S | 2025-07-19 | 2025-07-27 | CPD-NB-KM01-VBLU-54 (BIOD, 4R086A, HV 0.27VBLU, WAX4)
| PENDING ORDER |  |  |  |  | 2025-07-28 | 2025-07-20
72 | NB-AB-OLPF-032-SE-DAWN-OM6N | XS | S | S | S | 2025-07-01 | 2025-07-02 | CPD-NB-NT06-DAWN-05 (4HSD, WAX4)
| NB-AB-OLPF-032-SE-DAWN-OM6N | S | S | S | S | 2025-07-03 | 2025-07-13 | CPD-NB-NT06-DAWN-05 (4HSD, WAX4)
| MODIFICATION WORK - CLEANING & APM INSTAL |  |  |  |  | 2025-07-14 | 2025-07-19
| NB-AB-OLPF-032-SE-DAWN-OM6N | XS | S | S | S | 2025-07-20 | 2025-07-21 | CPD-NB-NT06-DAWN-05 (4HSD, WAX4)
| NB-AB-OLPF-032-SE-DAWN-OM6N | S | S | S | S | 2025-07-22 | 2025-07-29 | CPD-NB-NT06-DAWN-05 (4HSD, WAX4)
| PENDING ORDER |  |  |  |  | 2025-07-30 | 2025-07-31
Remarks:-
**Line 54 (26 Feb'22 onwards), Line 51 (26 Feb'22 onwards): Scale up of HSD filler.
**Line 49 (3 March'22 onwards), Line 55 (11 March'22 onwards), L57(18 March'22 onwards), L50 (24 March'22 onwards), L56(28 March'22 onwards) : Scale up of HSD filler.
**Line 59 (5 April'22 onwards), Line 58 (9 Arpil'22 onwards), Line 52 (13 Apil'22 onwards), Line 53 (12 Apil'22 onwards) : Scale up of HSD filler.
**Line 72 (11 April'22 onwards), Line 71 (13 April'22 onwards), L69 (16 April'22 onwards), L67 (22 April'22 onwards), L68 (23 April'22 onwards), L60 (31 May'22 onwards) : Scale up of HSD filler.
**Line 61 (2 May'22 onwards), Line 65 (5 May'22 onwards), L64 (14 May'22 onwards), L62 (20 May'22 onwards), L70 (22 May'22 onwards), L63 (23 May'22 onwards), L66 (27 May'22 onwards) : Scale up of HSD filler.
Reviewed by :
Date:
Approved by :
Date:
Note on A62: Nurul Aziani Binti Syaari: Delay MW
Note on C76: Nurul Aziani Binti Syaari: L66 - ASM4
Note on D76: Nurul Aziani Binti Syaari: L61 - Safedon
Note on F76: Nurul Aziani Binti Syaari: L61 - Safedon L66 - ASM4

## Sheet1
Line Number | Product Name | LB | LT | RB | RT | Start Date | End Date
49 | NB-AB-OLPF-033-SE-VIOL-ASTM | L | L | L | L | 2025-07-01 | 2025-07-03
50 | NB-AB-OLPF-030-SE-DKBU-EN6N | S | S | S | S | 2025-07-01 | 2025-07-01
51 | NB-AB-OLPF-027-SE-DKBU-ASTM | S | S | M | M | 2025-07-01 | 2025-07-05
52 | NB-AB-OLPF-027-SE-DKBU-ASTM | S | S | S | XS | 2025-07-01 | 2025-07-03
53 | NB-AB-OLPF-032-SE-MTBU-ACCF | S | S | M | M | 2025-07-01 | 2025-07-03
54 | NB-AB-OLPF-027-SE-MTBU-ASTM | XL | XL | L | L | 2025-07-01 | 2025-07-01
55 | NB-AB-OLPF-033-SE-VIOL-ASTM | S | S | S | S | 2025-07-01 | 2025-07-08
56 | NB-AB-OLPF-032-SE-VBLU-EN6N | M | M | M | M | 2025-07-01 | 2025-07-03
57 | NB-AB-OLPF-034-SE-VBLU-EN6N | M | M | M | M | 2025-07-01 | 2025-07-21
58 | NB-AB-OLPF-027-SE-MTBU-ASTM | S | S | S | S | 2025-07-01 | 2025-07-04
59 | NB-AB-OLPF-027-SE-MTBU-ASTM | M | M | M | M | 2025-07-01 | 2025-07-01
60 | NB-AB-OLPF-033-SE-VIOL-ASTM | M | M | M | M | 2025-07-01 | 2025-07-04
New Order Test
| Product Name | Size | Quantity | Due date
1 | NB-AB-OLPF-027-SE-WHTE-ASTM | L | 1152000 | 2025-08-01
2 | NB-AB-OLPF-027-SE-DKBU-ASTM | S | 4608000 | 2025-08-01
3 | NB-AB-OLPF-034-SE-WHTE-EN6N | S | 6336000 | 2025-08-01
4 | NB-AB-OLPF-034-SE-WHTE-EN6N | M | 6336000 | 2025-08-01
5 | NB-AB-OLPF-032-SE-WHTE-EN6N | S | 6336000 | 2025-08-01
6 | NB-AB-OLPF-032-SE-WHTE-EN6N | M | 6336000 | 2025-08-01
7 | NB-AB-OLPF-030-SE-VBLU-EN6N | XS | 3168000 | 2025-08-01
8 | NB-AB-OLPF-030-SE-VBLU-EN6N | S | 9504000 | 2025-08-01
Note on B14: Nurul Aziani Binti Syaari: Delay MW

## Pivot CPCF (hidden)
Plant 5 | [11 empty] | 11 | 19 | 9 | 11 | 19 |  |  | 19
Count of NGC Line #
Count of WDP | WDP | [6 empty] | Glove Code | Total | REV | Product type | CF1 | CF2 | CP | CPCF1 | CPCF2 |  |  | CF3 | FI | Grand Total
Start Date | CF | CF2 | CPCF2 | Grand Total |  |  |  | (blank) |  | REV 0 DRAFT@20.08 | 9 | 0 | 0 | 2 | 0 | 0 |  |  | 0 | 9 | 11
2025-07-04 | 1 |  |  | 1 |  |  |  | NO DEMAND | 4 | [11 empty] | 0
2025-07-06 |  | 1 |  | 1 |  |  |  | NB-AB-OLPF-027-SE-WHTE-ASTM | 4 | [11 empty] | 0
2025-07-07 |  |  | 1 | 1 |  |  |  | NB-AB-OLPF-035-SE-WHTE-EN6N | 11 | [11 empty] | 0
2025-07-08 |  | 1 |  | 1 |  |  |  | NB-AB-OLPF-040-SE-OBLU-EN6N | 4 | [11 empty] | 0
Grand Total | 1 | 2 | 1 | 4 |  |  |  | NB-AB-OLPF-027-SE-MTBU-ASTM | 1 | [11 empty] | 0
[8 empty] | NB-AB-OLPF-034-SE-GREY-ASTM | 5
[8 empty] | ANNUAL MAINTENANCE | 1 | REV 0 DRAFT@20.08 |  | 0 | 0 | 18 | 0 | 0 |  |  | 0 | 0 | 18
[8 empty] | PENDING ORDER | 10 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[8 empty] | NB-AB-OLPF-032-SE-LAVE-ASTM | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[8 empty] | NB-AB-OLPF-035-SE-OBLU-ASTM | 3 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[8 empty] | NB-AB-OLPF-034-SE-VBLU-EN6N | 6 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[8 empty] | NB-AB-OLPF-032-SE-WHTE-EN6N | 5 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
[8 empty] | NB-AB-OLPF-030-SE-WHTE-EN6N | 2
| 4 | 10 | 8 | 1 |  |  |  | NB-AB-OLPF-032-SE-VBLU-EN6N | 1
[8 empty] | Grand Total | 58
Plant 6
Count of WDP | WDP | [8 empty] | Count of NGC Line # |  |  | REV | Product type | CF1 | CF2 | CF3 | CF4 | CP | CPCF1 | CPCF2 | CF3 | FI | Grand Total
Start Date | CF | FICF | CF2 | CPCF | CF4 | FICF2 | Grand Total |  |  | Glove Code | Total |  | REV 0 DRAFT@20.08 | 11 |  | 3 |  | 1 | 22 | 2 | 2 |  | 4 | 34
01-Oct | 1 | [5 empty] | 1 |  |  | NB-AB-OLPF-032-SE-VBLU-EN6N | 17 |  | 0 | [10 empty] | 0
02-Oct |  |  | 1 |  |  |  | 1 |  |  | (blank) |  |  | 0 | [10 empty] | 0
03-Oct |  |  |  | 1 |  |  | 1 |  |  | NB-AB-OLPF-032-SE-DAWN-OM6N | 3 |  | 0 | [10 empty] | 0
07-Oct |  | 1 |  |  |  |  | 1 |  |  | ANNUAL MAINTENANCE | 1 |  | 0 | [10 empty] | 0
08-Oct |  |  |  |  | 1 |  | 1 |  |  | NB-AB-OLPF-035-SE-VBLU-EN6N | 3
09-Oct |  | 1 |  |  |  |  | 1 |  |  | MODIFICATION WORK | 1 |  | REV 0 DRAFT@20.08 |  | 0 | 57 |  |  | 198 | 22 | 38 | 0 | 0 | 315
14-Oct | 1 | [5 empty] | 1 |  |  | NB-AB-OLPF-032-SE-WHTE-EN6N | 2 |  | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
17-Oct | [5 empty] | 1 | 1 |  |  | PENDING ORDER | 9 |  | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
19-Oct | 1 | 1 |  |  |  |  | 2 |  |  | NB-AB-OLPF-034-SE-VBLU-EN6N | 10 |  | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
21-Oct | 1 | [5 empty] | 1 |  |  | NO DEMAND | 1 |  | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
25-Oct | 1 | [5 empty] | 1 |  |  | NB-AB-OLPF-035-SE-WHTE-OM6N | 4
27-Oct |  |  | 1 |  |  |  | 1 |  |  | NB-AB-OLPF-032-SE-WHTE-OM6N | 2
Grand Total | 5 | 3 | 2 | 1 | 1 | 1 | 13 |  |  | Grand Total | 53
| 5 | 3 | 4 | 1 | 4 | 2

## AM (hidden)
[6 empty] | Month | [13 empty] | Line Uptime (Hours) | Line Uptime (Month) | Last AM Date | Last AM Date | Status on 2024 | Proposed Date (2025) | Updated as of 17/1 | Remarks
HIK PROGRESS |  |  |  | Line |  | Feb'23 | Mar'23 | Apr'23 | May'23 | Jun'23 | Jul'23 | Aug'23 | Sep'23 | Oct'23 | Nov'23 | Dec'23 | Jan'24 | Feb'24 | Mar'24
|  |  |  | 61 | Plan | [14 empty] | 8936.39 | 12 | 19/11/2023 | 2025-01-20 | Awaiting for AM | 2025-02-20 | 2025-01-25 | *postpone AM to Feb'25 due to insufficent holder sparepart in Jan'25 proceed AM from 25/1
Line | Start | End | Status |  | Actual
49 |  |  |  | 62 | Plan | [14 empty] | 9741.84 | 14 | 23/10/2023 | Done - 20/10/2024 | DONE | 2025-11-20 | 2025-10-21
50 |  |  |  |  | Actual
51 |  |  |  | 63 | Plan | [14 empty] | 9351.22 | 13 | 2024-01-21 | Done - 21/01/2024 | DONE | 2025-03-20 | 2025-02-18
52 |  |  |  |  | Actual
53 |  |  |  | 64 | Plan | [14 empty] | 3175.92 | 4 | 2024-02-19 | Done -19/02/2024 | DONE | 2025-04-21 | 2025-03-22
54 | 2025-01-01 | 2025-01-10 | Completed |  | Actual
55 | 2025-02-09 | 2025-02-19 | Completed | 65 | Plan | [14 empty] | 43.8 | 0 | 2023-08-12 | Done - 21/09/2024 | DONE | 2025-10-20 | 2025-09-20
56 | 2025-02-04 | 2025-02-12 | Completed |  | Actual
57 |  |  |  | 66 | Plan | [14 empty] | 3294.34 | 5 | 2023-03-19 | Done -07/05/2024 | DONE | 2025-06-20 | 2025-05-21
58 |  |  |  |  | Actual
59 | 2025-01-04 | 2025-01-14 | Completed | 67 | Plan | [14 empty] | 845.12 | 1 | 2023-07-12 | Done 21/08/2024 | DONE | 2025-09-20 | 2025-08-21
60 |  |  |  |  | Actual
61 |  |  |  | 68 | Plan | [14 empty] | 2975.54 | 4 | 2023-04-10 | Done -20/06/2024 | DONE | 2025-07-20 | 2025-06-20
62 | - | - | ASM4 line |  | Actual
63 | 2025-03-01 | 2025-03-07 | Scheduled | 69 | Plan | [14 empty] | 4415.27 | 6 | 2024-04-02 | Done - 02/04/2024 | DONE | 2025-05-20 | 2025-04-20
64 |  |  |  |  | Actual
65 | 2025-03-01 | 2025-03-07 | Scheduled | 70 | Plan | [14 empty] | 687.2 | 1 | 2023-06-26 | Done - 21/07/2024 | DONE | 2025-08-20 | 2025-07-21
66 |  |  |  |  | Actual
67 |  |  |  | 71 | Plan | [14 empty] | 8551.22 | 12 | 2023-12-21 | Done - 22/12/2024 | DONE | 2026-01-20 | 2025-12-21
68 | - | - | ASM4 line |  | Actual
69 | 2025-02-18 | 2025-02-26 | Scheduled | 72 | Plan | [14 empty] | 10888.02 | 15 | 2023-09-20 | Done - 20/11/2024 | DONE | 2025-12-20 | 2025-11-20
70 |  |  |  |  | Actual
71 | 2025-01-01 | 2025-01-13 | Completed
72
[21 empty] | Line | Plan | Actual
[21 empty] | 49 | Aug | 2025-05-05
[21 empty] | 50 | Sep | 2025-09-01
[21 empty] | 51 | Oct | 2025-10-01 |  |  |  |  | SO | CETD | (cs) |  |  |  | ('000 pcs) |  |  |  | PM status | FG code | Glove Code
[21 empty] | 52 | Nov | 2025-11-01 | [6 empty] | S | M | L | XL | S | M | L | XL
[21 empty] | 53 | Dec | 2025-12-01 |  |  |  |  | PMEC 38/25 | 2025-03-20 | 0 | 1521 | 0 | 0 |  | 3802.5 | 0 | 0 | Purchased | FG-PMEC-0023 | NB-AB-OLPF-032-SE-LSBU-ASTM
[21 empty] | 54 | Jan | 2025-01-01 |  |  |  |  | PMEC 44/25 | 2025-03-25 | 0 | 1000 | 0 | 0 | 0 | 2000 | 0 | 0 | Purchased | FG-PMEC-0016 | NB-AB-OLPF-032-SE-LSBU-ASTM
[21 empty] | 55 | Feb | 2025-02-09 |  |  |  |  | PMEC 43/25 | 2025-03-26 | 2332 | 400 | 0 | 0 | 4664 | 800 | 0 | 0 | Purchased | FG-PMEC-0016 | NB-AB-OLPF-032-SE-LSBU-ASTM
[21 empty] | 56 | Mar | 2025-03-01 |  |  |  |  | PMEC 45/25 | 2025-03-26 | 250 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | Purchased | FG-PMEC-0016 | NB-AB-OLPF-032-SE-LSBU-ASTM
[21 empty] | 57 | Apr | 2025-04-02 |  |  |  |  | PMEC 45/25 | 2025-03-26 | 0 | 172 | 0 | 0 | 0 | 430 | 0 | 0 | Purchased | FG-PMEC-0013 | NB-AB-OLPF-032-SE-LSBU-ASTM
[21 empty] | 58 | May | 2025-06-01 |  |  |  |  | PMEC 42/25 | 2025-03-27 | 2332 | 400 | 0 | 0 | 4664 | 800 | 0 | 0 | Purchased | FG-PMEC-0016 | NB-AB-OLPF-032-SE-LSBU-ASTM
[21 empty] | 59 | June | 2025-07-01 |  |  |  |  | PMEC 41/25 | 2025-03-27 | 2332 | 400 | 0 | 0 | 4664 | 800 | 0 | 0 | Purchased | FG-PMEC-0016 | NB-AB-OLPF-032-SE-LSBU-ASTM
[21 empty] | 60 | July | 2025-08-01 |  |  |  |  | KWNS 04/25 | 2025-04-02 | ('000 pcs) M: 500 | Purchased | FG-KWNS-0004 | NB-AB-OLPF-035-SE-WHTE-EN6N

## Product Color (hidden)
Product Color
NB-AB-OLPF-027-SE-WHTE-ASTM | S | M | L | XL
NB-AB-OLPF-030-SE-WHTE-EN6N | S | M | L | XL
NB-AB-OLPF-032-SE-WHTE-EN6N | S | M | L | XL
NB-AB-OLPF-035-SE-WHTE-EN6N | S | M | L | XL
NB-AB-OLPF-027-SE-OBLU-ASTM | S | M | L | XL
NB-AB-OLPF-030-SE-OBLU-EN6N | S | M | L | XL
NB-AB-OLPF-035-SE-OBLU-ASTM | S | M | L | XL
NB-AB-OLPF-040-SE-OBLU-EN6N | S | M | L | XL
NB-AB-OLPF-030-SE-VBLU-EN6N | S | M | L | XL
NB-AB-OLPF-032-SE-VBLU-EN6N | S | M | L | XL
NB-AB-OLPF-035-SE-VBLU-EN6N | S | M | L | XL
NB-AB-OLPF-027-SE-DKBU-ASTM | S | M | L | XL | INACTIVE
NB-AB-OLPF-030-SE-DKBU-EN6N | S | M | L | XL | INACTIVE
NB-AB-OLPF-032-SE-DKBU-EN6N | S | M | L | XL
NB-AB-OLPF-035-SE-WHTE-OM6N | S | M | L | XL
NB-AB-OLPF-032-SE-WHTE-OM6N | S | M | L | XL
NB-AB-OLPF-032-SE-DAWN-OM6N | S | M | L | XL
NB-AB-OLPF-027-SE-TTBU-ASTM | S | M | L | XL
NB-AB-OLPF-035-SE-VBLU-ASTM | S | M | L | XL | OBSOLETE
NB-AB-OLPF-032-SE-MTBU-ACCF | S | M | L | XL
NB-AB-OLPF-027-SE-DCBU-ASTM | S | M | L | XL
NB-AB-OLPF-034-SE-GREY-ASTM | S | M | L | XL
NB-AB-OLPF-038-SE-GREY-ASTM | S | M | L | XL
NB-AB-OLPF-032-SE-LAVE-ASTM | S | M | L | XL
NB-AB-OLPF-027-SE-MTBU-ASTM | S | M | L | XL
NB-AB-AMPF-030-SE-VBLU-EN6N | S | M | L | XL
NB-AB-OLPF-032-SE-TUGR-BDOM | L | M | M | M
NB-AB-OLPF-034-SE-VBLU-EN6N | L | M | M | M
NB-AB-OLPF-035-SE-VBLU-BIOD | L | M | M | M
NB-AB-OLPF-035-SE-DAWN-OM6N | S | M | L | XL
NB-AB-OLPF-032-SE-LSBU-EN6N | S | M | L | XL | P6
NB-AB-OLPF-033-SE-VIOL-ASTM | S | M | L | XL | P5
NB-AB-OLPF-037-SE-DBLU-EN7N | S | M | L | XL | P6
NB-AB-OLPF-037-SE-LVBU-EN6N | S | M | L | XL | P6
NB-AB-AMPF-032-SE-VBLU-EN6N | S | M | L | XL
NB-AB-OLPF-037-SE-DBLU-EN7N | S | M | L | XL